Timeline – EUPF Seminar 2022

| Week | Planning |
| --- | --- |
| 23 – 24 May 2022 | 18th Annual EU UN-Procurement Seminar |
| May 16th | Inform Companies about their complete meeting schedule |
| May 12th | Last day for UN to request changes in schedules |
| May 6th | Inform UN representatives about their schedules |
| April 28th | Last day for companies to cancel because of lack of meetings; start planning 1-on-1 meetings |
| April 22nd | Final deadline registration (without 1-on-1 meeting requests) |
| April 19th | Deadline to inform companies about their 1on1 meeting assignments |
| April 14th | Final feedback UN Organizations on company profiles & availability; inform companies about feedback UN; Last day to accept B2B meetings |
| March 25th | Final deadline registration to be eligible for 1-on-1’s; go/no go decision |
| March 22nd | 3rd Webinar (tentative) |
| March 8st | 2nd Webinar (tentative date) |
| March 7th | End of Country cap (10 per country) |
| February 25th | End of Early Bird discount (unless first 35 participants have been reached) |
| February 22nd | 1st Webinar (tentative date) |
| February 14th | Invite other UN Organizations |
| February 7th | Registration opens |
| January 24th | Send Invitations Chiefs UNO’s (UN/PD / UNDP) |
| January 24th | EUPF Website updated |

In-person option